## Project plan
Project name | Party Maker
Task Name | Project Owner | Developers/ Executors | Status | Start Date | Initially planned End date | Actual/Expected End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete
1. Initiation | Kristupas | Everyone | Completed | 2019-10-02 | 2019-10-13 | 2019-10-13 | 11 | 11 | 0 | 100%
2. Requirements + UX | Kristupas | Kristupas | Completed | 2019-10-21 | 2019-10-28 | 2019-10-28 | 7 | 7 | 0 | 100%
3. UI | Kristupas | Vaidotas/Karolis | Completed | 2019-10-18 | 2019-12-06 | 2019-10-21 | 3 | 2.4 | 0.6 | 80%
4. Programming works | Kristupas | Žygimantas/Karolis | Completed | 2019-10-21 | 2019-12-06 | 2019-12-28 | 68 | 68 | 0 | 100%
5. Deployment to server | Kristupas | Karolis/Žygimantas | Completed | 2019-12-06 | 2019-12-23 | 2019-12-28 | 22 | 22 | 0 | 100%
6 Testing | Kristupas |  | In process | 2019-12-23 | 2020-01-04 | 2019-12-29 | 6 | 3 | 3 | 50%
5. Project closure | Kristupas |  | In process | 2019-12-15 | 2020-01-04 | 2020-01-04 | 20 | 18 | 2 | 90%