## Project plan
Project name | Party Maker
Task Name | Project Owner | Developers/ Executors | Status | Start Date | Initially planned End date | Actual/Expected End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete
1. Initiation | Kristupas | Everyone | Completed | 2019-10-02 | 2019-10-13 | 2019-10-13 | 11 | 11 | 0 | 100%
2. Requirements + UX | Kristupas | Kristupas | Completed | 2019-10-13 | 2019-10-28 | 2019-10-22 | 9 | 9 | 0 | 100%
3. UI | Kristupas | Vaidotas/Karolis | Completed | 2019-10-21 | 2019-11-06 | 2019-10-28 | 7 | 7 | 0 | 100%
4. Programming works | Kristupas | Žygimantas/Karolis | Completed | 2019-10-18 | 2019-12-16 | 2019-12-20 | 63 | 56.7 | 6.3 | 90%
5. Deployment to server | Kristupas | Karolis/Žygimantas | Completed | 2019-11-29 | 2019-12-23 | 2019-12-06 | 7 | 7 | 0 | 100%
6 Testing | Kristupas | Karolis/Kristupas | Completed | 2019-12-13 | 2019-12-31 | 2019-12-26 | 13 | 3.9 | 9.1 | 30%
7. Project closure | Kristupas |  | Completed | 2019-12-21 | 2020-01-04 | 2019-12-28 | 7 | 0 | 7 | 0%